## digrammatic project plan
week beginning | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | Milestones | Deliverables
task number | wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | cv1 | cv2 | cv3 | cv4 | wk12 | wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | ev1 | ev2 | ev3 | ev4 | wk 12
1 | [32 empty] | Review literature on FK/IK, redundancy, kinematics, skill transfer | Project plan, risk and ethics assessment | bar: 2025-09-29 to 2025-11-17
2 | [32 empty] | KUKA iiwa 14 configured in Isaac Lab with 3 configurations: 5, 6, 7 DOF | bar: 2025-10-13 to 2025-10-20
3 | [32 empty] | Set up the ROS2 / ROS bridge environment and connect to the iiwa model. | Robot simulation and basic control are prepared and ready to be used for generating training data and testing models in simulation. | bar: 2025-10-27 to 2025-11-03
4 | [32 empty] | Grid datasets for 5, 6 and 7 DOF generated | bar: 2025-11-10 to 2025-11-17
5 | [32 empty] | Train residual MLP FK and IK models for 5, 6 and 7 DOF using the generated datasets | Complete set of joint–pose CSV files and corresponding trained FK/IK model | bar: 2025-11-17 to 2025-12-01
6 | [32 empty] | Calculate and convert normalised loss into actual loss | bar: 2025-12-01
7 | [32 empty] | Prepare summary tables and learning curves | Summary tables and loss curves for 5,6, and 7 DOF for evaluation | bar: 2025-12-01 to 2025-12-08
8 | [32 empty] | Implement a model-agnostic meta-learning (MAML-style) algorithm | bar: 2025-12-15 to 2025-12-29
9 | [32 empty] | Train a meta-initialisation that adapts quickly to each DOF as separate tasks | bar: 2025-12-22 to 2026-02-09
10 | [32 empty] | Explore adaptation to unseen DOFs (<5 or >7) | Meta-learning results (loss curves, adaptation plots) and comparison against separately trained FK/IK models. | bar: 2026-02-16 to 2026-02-23
11 | [32 empty] | validate the meta-learned FK in simulation | bar: 2026-02-16 to 2026-03-23
14 | [32 empty] | Final Report Writing | Final report including simulation and real-robot evaluation, sim-to-real analysis and conclusions. | bar: 2026-03-23 to 2026-05-04